## Sheet1
Address Work Details (Inc Postcode) | Traffic Control | Work Status | Estimated Start Date | Latest/Actual Start Date | Estimated End Date
HARDENS MEAD, CHIPPENHAM | Some Carriageway Incursion | Works Stop (With Excavation) | 2021-03-11 | 2021-03-15 | 2021-03-26
BOWOOD CLOSE, DERRY HILL | Some Carriageway Incursion | Works Stop (With Excavation) | 2021-03-15 | 2021-03-16 | 2021-03-29
LANSDOWNE CRESCENT, DERRY HILL | Some Carriageway Incursion | In Progress | 2021-03-17 | 2021-03-22 | 2021-04-06
LANSDOWNE CRESCENT, DERRY HILL | Some Carriageway Incursion | In Progress | 2021-03-17 | 2021-03-17 | 2021-03-30
KERRY CLOSE, DERRY HILL | Some Carriageway Incursion | In Progress | 2021-03-19 | 2021-03-25 | 2021-04-09
Fitzmaurice Close, Derry Hill | Some Carriageway Incursion | In Progress | 2021-03-19 | 2021-03-25 | 2021-04-09
REDHILL CLOSE, DERRY HILL | Some Carriageway Incursion | In Progress | 2021-03-24 | 2021-03-24 | 2021-04-06
WYCOMBE CLOSE, DERRY HILL | Some Carriageway Incursion | In Progress | 2021-03-26 | 2021-03-29 | 2021-04-09
SHELBURNE WAY, DERRY HILL | Some Carriageway Incursion | In Progress | 2021-03-26 | 2021-03-29 | 2021-04-09
DEVIZES ROAD, DERRY HILL | Traffic Control (Two-Way Signals) | PERMIT-GRANTED | 2021-03-30 | 2021-04-05 | 2021-04-12
Church Road, Derry Hill | Traffic Control (Two-Way Signals) | Early Start Requested | 2021-04-01 | 2021-04-07 | 2021-04-14
LONDON ROAD, CHIPPENHAM | Traffic Control (Multi-Way Signals) | PERMIT-GRANTED | 2021-04-05 | 2021-04-09 | 2021-04-16
A4 South East from Pewsham roundabout to junction with A342 | Traffic Control (Two-Way Signals) | PERMIT-GRANTED | 2021-04-08 | 2021-04-14 | 2021-04-21
Old Derry Hill, Calne | Traffic Control (Two-Way Signals) | PERMIT-GRANTED | 2021-04-08 | 2021-04-14 | 2021-04-21
STANLEY LANE, STANLEY | Road Closure | PERMIT-GRANTED | 2021-04-26 | 2021-04-30 | 2021-04-30
STANLEY LANE, STANLEY | Road Closure | PERMIT-GRANTED | 2021-05-03 | 2021-05-04 | 2021-05-05
BENCROFT FARM EAST TO JUNCTION WITH C113, BREMHILL | Road Closure | PERMIT-GRANTED | 2021-05-05 | 2021-05-11 | 2021-05-10
BENCROFT HILL, STANLEY | Road Closure | PERMIT-GRANTED | 2021-05-05 | 2021-05-11 | 2021-05-10
STUDLEY HILL TO STANLEY LANE, STANLEY | Road Closure | PERMIT-GRANTED | 2021-05-14 | 2021-05-20 | 2021-05-17
Junction with A4 north to Studley Hill | Road Closure | PERMIT-GRANTED | 2021-05-18 | 2021-05-24 | 2021-05-28
STUDLEY HILL, STUDLEY | Road Closure | PERMIT-GRANTED | 2021-05-31 | 2021-06-04 | 2021-06-11
STUDLEY HILL TO STANLEY LANE, STANLEY | Road Closure | PERMIT-GRANTED | 2021-05-31 | 2021-06-04 | 2021-06-11
Norley Lane, Studley | Road Closure | PERMIT-GRANTED | 2021-06-14 | 2021-06-18 | 2021-06-25
Church Road | Road Closure | PERMIT-GRANTED | 2021-06-28 | 2021-07-02 | 2021-07-09
OLD ROAD, STUDLEY | Road Closure | PERMIT-GRANTED | 2021-07-12 | 2021-07-16 | 2021-07-27